## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Create database | 5 | 1 | 2024-01-02
2 | Create and host website | 2 | 1 | 1
3 | Registration page design | 2 | 1 | 1
4 | Home/book page design | 2 | 1 | 1
5 | Login page design | 2 | 1 | 1
6 | Connect accounts to database | 3 | 1 | 2
7 | User authentication (Login) | 2 | 2 | 2
8 | User creation (Registration) | 2 | 2 | 2
9 | Store user info in database | 4 | 2 | 2
10 | Add book (frontend) functionality | 3 | 2 | 2
11 | Delete book (frontend) functionality | 3 | 2 | 2
12 | Welcome page design | 2 | 4 | 2
13 | Store renter info (name/email) in database | 4 | 2 | 3
14 | Store books in database | 3 | 2 | 3
15 | Edit book status | 2 | 3 | 3
16 | Delete book backend functionality | 2 | 3 | 3
17 | Implement email reminder system | 5 | 3 | 3
18 | Filteration system | 2 | 3 | 3
19 | Update PWEB | 2 | 4 | 3
20 | API scanner to add/search books | 5 | 4 | N/A
21 | User profile to edit or delete profile | 3 | 4 | N/A