## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Create database | 5 | 1 | 1
2 | Login page design | 2 | 1 | 1
3 | Registration page design | 2 | 1 | 1
4 | Home page design | 2 | 1 | 1
5 | Connect database to website | 2 | 1 | 1
7 | Connect accounts to database | 3 | 1 | 2
8 | User authentication (Login) | 2 | 2 | 2
9 | User creation (Registration) | 2 | 2 | 2
10 | Store books in database | 3 | 2 | 2
11 | Store user info in database | 4 | 2 | 2
12 | Store renter info (name/email) in database | 4 | 3 | 2
13 | Implement email reminder system | 5 | 3 | 2
14 | User profile to edit or delete profile | 3 | 4 | 3
15 | Welcome page design | 2 | 4 | 3
16 | Update PWEB | 2 | 4 | 3
6 | API scanner to add/search books | 5 | 4 | 3